## safety list pre delivery
| project | detail | date done
1 | ac remove to get to engine controls/guages in main cabin
2 | anchor - remove plow and add bruce and rode
3 | anchor and rode stern install
4 | anchor windlass base fix cracks
5 | back stay adjustment
6 | batteries remove and replace 2 size 34 dead |  | 2017-10-16
7 | batteries remove and replace two 4d dead |  | 2017-10-15
8 | battery boxes, wiring and secure boxes
9 | battery switches and mount higher on wall replace and move
10 | bilge - clean and inspect
11 | bilge pumps electric and manual test, rebuild or rewire all
12 | boom 2x6 supports |  | 2016-11-25
13 | boom vang add
14 | bow windlass manual levers/handles
15 | chain locker dam
16 | charger and inverter check
17 | cockpit anchor buttons test and verify
18 | cockpit drains unplug and fix duct tape |  | 2016-11-24
19 | cockpit rear drain fix leak and duct tape
20 | cruiseair compressors remove from engine room
21 | depth transducer mount in bow and install back up GPS - mount new
22 | electric winch stern test and clean contacts
23 | engine room add 12 volt lights
24 | garmin and autopilot relocate to within rails
25 | gps and radar test
26 | halyards replace three
27 | head and hose remove 3 way
28 | head holding tank for aft head add
29 | jib find roller furler 130 jib | Bacon UK kevlar tape with foam & UV | 2017-10-31
30 | jib furling lubricate and rerig to port for stbd UV cover
31 | lifeline gate and check old replace w 7mm sts- wrr
32 | liferaft check or replace
33 | light fixtures 110v wire into outlets and switch to LED
34 | main sail furling - strip, repair and lube
35 | mainsail battcar installation hardware | hobie mast sections, cut and tap, screws long for prefit
36 | mainsail find roller furl main | Bacon Mercer 44 North New | 2017-10-30
37 | mainsail for battcar | gromets every 3 to 4 feet
38 | mast step check from inside, strip loose paint and repaint
39 | mast sump vacuum and clean |  | 2016-11-24
40 | microwave and household ac remove
41 | onan seafoam and fog oil into inlet manifold or remove
42 | power wash deck, cabin teak, toe rail and hull |  | 2016-11-24
43 | prop shaft brake check
44 | prop shaft zinc R&R
45 | propane locker clean and clear drain
46 | propane locker lid recore and reglue
47 | propane solonoid and bypass
48 | propane stove clean and test
49 | propane tank add pressure guage
50 | propane tank fill
51 | rib leak and outboard check
52 | running lights led bulbs
53 | seacocks cap off all unused | 2 cockpit drains, engine and onan inlet, 2 sink drains, 2 shower
54 | seacocks free and grease all
55 | shift and kill cables measure and replace
56 | spreader end boots and tape
57 | steering pedestal, cable and chain lube
58 | throttle cable remove and replace
59 | tiller find and test emergency steering
60 | topping lift and outhaul replace
61 | topping lift safety line from cable
62 | TV remove, add new antenna |  | 2016-11-25
63 | vhf antenna deck backup
64 | vhf repower
65 | water tank - suck clean and measure |  | 2016-11-26
66 | whisker poles free up and lube | 1 of 2 | 2016-11-26
67 | winch for topping lift on starboard companionway replace or test with line
68 | winches clean and grease
69 | windlass spring, add midship battery with separate charger and re wire

## engine project list
| project | detail | date done
1 | alternator check | rusted & had bearings froze
2 | alternator remove and replace | verify wiring
3 | bilge clean and prime white paint | vacuum shoe box debris from engine | 2016-11-25
4 | bleed fuel and hook temp water supply |  | 2016-11-26
5 | coolant - flush and refill
6 | cylinder head laser temp check
7 | day diesel tank use tom sawyer, browning or tanzer | mount where onan was
8 | diesel lines and filters - drain and refill
9 | diesel tank - drain, clean and refill
10 | diesel tank level check process | stick and 3/8 plug
11 | engine control panel at binocular box add
12 | fuel filter remove and replace with seafoam |  | 2016-11-25
13 | key switch and push buttons clean existing
14 | motor oil and filters - drain and refill | 9 qts and crushed frozen filter sucked from front 7/8 plug | 2017-11-25
15 | muffler loose insulation
16 | onan generator - remove & lower
17 | power and start switch add parallel 4 way key switch
18 | primary fuel filter clean and new filter
19 | raw water strainer relocate and replace
20 | reduction gear - drain and refill lube
21 | starter remove and replace |  | 11/9 &11/26
22 | temp 1 gal fuel supply with seafoam |  | 2016-11-26
23 | throttle, shift, kill cables replace/lube
24 | trans/gear box - drain and refill hyd fluid
25 | trans/gear box - add oil temp and pressure gauge
26 | valve cover remove and de hyd block |  | 2016-11-25
27 | water inlet hose - remove and replace 1 id 1.5od 70in
28 | water pump impellers remove and replace both

## cosmetic list
| project | detail | date done
1 | aft cabin floor remove rotten and fill
2 | aft cabin stbd side hull
3 | bulkhead at floor back of forward shower drill epoxy and screw tight and fill
4 | cabin sole aft of mast shave and fill
5 | door aft cabin - lower edge loose
6 | engine room clean and paint
7 | fore cabin port side vertical and lid of closet
8 | hull rub rail - clean and silicon gap
9 | Insulate aft and fore cabin walls
10 | mast and boom paint
11 | mount flatscreen T V
12 | port exterior rebed or clean and silicon around top
13 | port rain deflecters - silicon lower half
14 | route tv cable
15 | shower basin caulk/gap filler
16 | teak veneer around cabin window cut rotten, insulate and vinyl cover
17 | upper and lower cabin side molding remove, sand and varnish

## comfort
| project | detail | date done
1 | aft cabin berth
2 | cabin lights - main cabin aft & fore
3 | install aft holding tank with pump out
4 | install proheat, hose, water heater and 6 heater cores
5 | install propane pressure meter , refill tanks and do solonoid, clean stove
6 | refridge and freezer flush, refill and leak test
7 | replumb both heads
8 | test water pressure system